## Risk Assessment
RISK ASSESSMENT — Wayne Enterprises ¦ Insider Threat: Confidential Data Leak
Prepared by: Artsiom Pankrashkin ¦ Risk Score = Likelihood × Impact ¦ Estimated Financial Loss: $700,000
IMPACT SCALE |  |  | LIKELIHOOD SCALE |  |  | RISK LEVEL GUIDE
Scale | Rating | Description | Scale | Rating | Description | Score | Level & Meaning
3 | High | Over $500K | 3 | Likely | Already happened | 6 – 9 | HIGH — Unacceptable, immediate treatment required
2 | Medium | $100K – $499K | 2 | Possible | May happen | 4 – 5 | MEDIUM — Needs mitigation or justification
1 | Low | Under $100K | 1 | Unlikely | Very rare | 1 – 3 | LOW — Acceptable, monitor and review
RISK REGISTER
# | Risk Description | Likelihood | Impact | Risk Score | Risk Level | Recommended Treatment | Owner
1 | Employee deliberately leaked confidential salary data to a competitor | Likely (3) | High (3) | 9 | HIGH | Forensic investigation, revoke all access immediately, notify legal & HR | IT Security + HR
2 | No DLP controls — second employee could repeat the same leak undetected | Likely (3) | High (3) | 9 | HIGH | Deploy DLP solution, block unauthorised transfers to USB/personal email/cloud | IT Security
3 | Legal and regulatory exposure from the salary data breach | Likely (3) | High (3) | 9 | HIGH | Engage legal counsel, notify affected staff, review data protection compliance | Legal + Compliance
4 | Competitor uses leaked salary data to recruit key Wayne Enterprises staff | Likely (3) | High (3) | 9 | HIGH | Brief leadership, review compensation, monitor resignation patterns | HR + Leadership
5 | Residual risk after compensating control reduces likelihood to scale 1 | Unlikely (1) | High (3) | 3 | LOW | Maintain access controls, DLP and UEBA monitoring. Review annually. | IT Security
QUIZ ANSWERS
# | Question | Correct Answer | Score Workings
Q1 | What is the risk score? (Assuming it has already occurred) | 9 | Likelihood: Likely (3) × Impact: High (3) = 9
Q2 | Based on the risk score, Wayne Enterprises should: | Propose immediate risk treatment | Score 9 = HIGH → Unacceptable → Immediate treatment required
Q3 | After a compensating control reduces Likelihood to 1, the risk is: | Acceptable | New score: 1 × 3 = 3 = LOW → Acceptable
Note: The course template labels Risk Score 2–5 as Medium. However Q3 confirms that a score of 3 (1×3) is LOW/Acceptable — so the correct bands are: 1–3 = Low, 4–5 = Medium, 6–9 = High.